## Sheet1
S.No. | Description | Resolution | Code File Impacted | DB Scripts Impacted | Status | Start Date | End Date
1 | Session not being cleared at signout. User can still access portal by simply pressing back button from browser. | Session is cleared out at logout action method. | UserController.cs | N.A. | Resolved | 2017-12-28 | 2017-12-28
2 | Passwords are being stored in open texts inside database. | Added methods for encryption in website and columns in database to apply the change. Also, login calls for web/mobile API were modified. | ServiceGetUserData.cs GetSetEmployee.cs GetSetUser.cs CommonMethods.cs | UserMaster | Resolved | 2017-12-29 | 2018-01-04
3 | If session is cleared by IIS, user is not routed to login page. Instead, action method gets executed and displays unexpected results. | A session filter is created and applied to all controllers | All controllers | N.A. | Resolved | 2018-01-02 | 2018-01-02
4 | Dropdowns in Add New Brand module contain default select list item in different order | Dropdowns were being generated on basis of text value rather than the index of select list item. | Brand\Manage.cshtml | N.A. | Resolved | 2018-01-04 | 2018-01-04
5 | On Dashboard, PJP Efficiency tab, if we need to get data of one day, say 10 Jan, then user needs to input start date as 10 Jan and end date as 11 Jan, whereas both should be entered as 10 Jan | At server's end, date time is being generated as 00:00:00 for end date as well. Fixed it to 23:59:59 to cover whole day. | UserController.cs | N.A. | Resolved | 2018-01-11 | 2018-01-11
6 | Actual Unplanned count is incorrect on dashboard's PJP Efficiency tab. | A very complex LINQ query is seen. Moved it to a new procedure with better approach and correct output. | GetDashboard.cs | Pro_Web_ActualCallsUnplanned | Resolved | 2018-01-10 | 2018-01-11
7 | Shop Visit Report has multiple records. | If there is a network issue, a new record was created on next update from mobile. Instead, existing record should be updated. | ServiceGetInventoryStore.cs | N.A. | Resolved | 2018-01-11 | 2018-01-12
8 | Images missing in few records for Stock Report | same as above | same as above | same as above | Resolved | 2018-01-11 | 2018-01-12
9 | Segment name column is empty in Plan vs Actual vs Agreed Report if downloaded in Excel | Segment name not being updated in code and also not being fetched from database. | GetReportPlanvsActualvsAgreed.cs | Pro_RPT_PlanVsActualVsAgreed | Resolved | 2018-01-16 | 2018-01-16
10 | Lat/Long difference while update being pushed from mobile app for customer info |  |  |  | Pending | 2018-01-16
11 | If user checks in for a licensee from app, sometimes a scenario occurs where in api receives data and creates a new record in database for the same. However, user at mobile end was unable to check in and reach check list due to some unkown issues related to network. Hencec if the user tries to check in again, a message is shown that user has already checked in for the day. | Added another check to see if database received a record for check in but due to network issue response was not received by the end user. In this case we have a record in database with a check in value but no check out value. Due to the presence of this record, user was not able to check in again. Hence an if condition is applied to consider check out time as well while checking in. | ServiceGetSetCustomerCheck_InOut.cs | N.A. | Resolved | 2018-01-17 | 2018-01-18
12
13
14
15
16
17
18
19
20
21
22
23
24
25